EVERETT SCHOOL DISTRICT

PEP GRANT TIMELINE YEAR 2

| Projected Date |  |  | Item | Notes | Actual Date |
| --- | --- | --- | --- | --- | --- |
| ES | MS | HS |  |  |  |
| Aug 26 | Aug 26 | Aug 26 | Focused Fitness K-12 Training | 8-3 @ Longfellow (ALL) |  |
| Sept 3 | Sept 3 | Sept 3 | Begin Fitness Pre-Test | 5th,8th, 9th grade required (Height & Weight, Pacer, Sit & Reach, Curl-ups, Push-ups) – all other grades optional but encouraged |  |
| Oct 31 | Oct 17 | Oct 17 | Fitness Pre-assessment Data complete | Fitness Pre-assessments Data entered into WEL-PRO |  |
| Sept 30, Oct 1 | Sept 30, Oct 1 | Sept 30, Oct 1 | Focused Fitness K-12 Training | Sept. 30, Middle School Oct. 1 Elem, High Grade level training |  |
| Pre: Sept 17 Post: Nov 7 | Pre: Sept 19 Post: Oct 10 | Pre: Sept 19 Post: Post Oct 10 | Five Components of Fitness Unit pre-assessment / post-assessment | 5th, 8th, 9th grade required Basic book pages 1.9 – 1.10 pre and post-assessments to be completed and recording sheets (pre and post score list only as number correct posted on class list with students ID# and name) delivered to _Robert____ by __________ |  |
| Nov 18/19 | Nov 18/19 | Nov 18/19 | Focused Fitness K-12 Training | South Nov 18, North Nov 19 |  |
| Sept 30 | Sept 30 | Sept 30 | Student Pre-Survey 1st Semester Post Jan 20 | 5th, 8th, 9th grade required Bring students into computer lab go to www.focusedfitness.org click on WEL-PRO link, click on surveys, click on student survey (students need to have student ID#) |  |
| Jan 13/14 | Jan 13/14 | Jan 13/14 | Focused Fitness K-12 Training | Jan 13, Elem, High; Jan 14, Middle School |  |
| August 26 | August 26 | August 26 | Teacher Pre-Survey | Done at training (if not completed, go to www.focusedfitness.org click on WEL-PRO link click on surveys, click on teacher survey) |  |
| Oct 30 | Oct 30 | Oct 30 | Activity Log on WEL-PRO | 5th, 8th, 9th grade www.focusedfitness.org click on WEL-PRO link behavior logs, activity log / three days (Two week days and one weekend day) |  |
| Mar 10/11 | Mar 10/11 | Mar 10/11 | Focused Fitness K-12 Training | March 10, South; March 11, North |  |
| Feb 11 | Jan 31 | Jan 31 | Activity Log (Hard copy or on WEL-PRO) | 5th, 8th, 9th grade required www.focusedfitness.org click on WEL-PRO link behavior logs, activity log / three days (Two week days and one weekend day) |  |
| Pre: Feb 6 Post: March 13 | Pre: Dec 8 Post: Jan 6 | Pre: Feb 5 Post: March 20 | Food for Energy and Health Unit pre-assessment / post-assessment | 5th, 8th, 9th grade Food for energy and Health unit – Basic book assessment on pages 2.31-2.32 pre and post to be completed and recording sheets (pre and post score list only as number correct posted on class list with students ID# and name) delivered to __ Robert by __________ |  |
| May 12/13 | May 12/13 | May 12/13 | Focused Fitness K-12 Training | May 12, Middle; May 13, Elem, High |  |
| May 31 | May 31 | May 31 | Activity Log (Hard copy or on WEL-PRO) | 5th, 8th, 9th grade www.focusedfitness.org click on WEL-PRO link behavior logs, activity log / three days (Two week days and one weekend day) |  |
| May 29 | April 24 | May 15 | Washington State CBA |  |  |
| March 31 | March 31 | March 31 | Activity Log (Hard copy or on WEL-PRO) | 5th, 8th, 9th grade three days (Two week days and one weekend day) |  |
| June 12 | June 3 | June 3 | Student Post-Survey | 5th, 8th, 9th grade Bring students into computer lab go to www.focusedfitness.org click on WEL-PRO link, click on surveys, click on student survey (students need to have student ID#) |  |
| May 13 | May 12 | May 13 | Teacher Post-Survey | www.focusedfitness.org click on WEL-PRO link click on surveys, click on teacher survey (Will complete during training) |  |
| April 6-June 12 | April 6- June 10 | April 6- June 10 | Post Fitness measurements completed and all data sent in | 5th, 8th, 9th grade (Height & Weight, Pacer, Sit & Reach, Curl-ups, Push-ups) – all other grades optional but encouraged Fitness Post-assessments to be completed and recording sheets with students ID # and name delivered to _Robert____ curriculum by __________ |  |
| June 16 | June 16 | June 16 | Student/Parent Post-Fitness assessment Reports | Send home with report cards |  |
| June 4, 5 | June 4, 5 | June 4, 5 | Focused Fitness K-12 Training | ALL |  |
| July | July | July | Five for Life Summer Institute | Watch for Invitation via e-mail in May /June and sign up then |  |